## PreDeploymentSteps
No | Salesforce Mode | Description | Steps | Responsible | User Story | Time | CI | QA | UAT | PROD | Reference
1 | Classic | Update Shaing Settings | Goto -> Setup -> Administer -> Security Controls - Sharing Settings Click Button "Enable External Sharing Model" Click Edit in "Organization-Wide Defaults" Section as follows Account - Default Internal Access - Public Read / Write Account - Default External Access - Private Contact - Default Internal Access - Private Contact - Default External Access - Private Opportunity - Default Internal Access - Private Opportunity - Default External Access - Private Click Save
2 | Classic | Enable Relate Contact to Multiple Accounts | Goto -> Setup -> Build -> Customize -> Accounts -> Account Settings Click Edit Goto Section "Contacts to Multiple Accounts Settings" Select check box against "Allow users to relate a contact to multiple accounts" Click Save
3 | Classic | Enable Email Deliverability | This step is required only for sandboxes Goto -> Setup -> Administer -> Email Administration -> Deliverability Goto Section Deliverability Change Access Level to "All Emails" Click Save
4 | Classic | Update Case Reason Picklist | Goto -> Setup -> Build -> Customize -> Cases -> Fields Click Field "Case Reason" Goto Section "Case Reason Picklist Values" Click New Enter "Volunteer De-Registration" Click Save
5 | Classic | Create my domain | Goto Setup -> Administer -> Domain Management -> My Domain Click Log in (Right side panel) Click Deploy to Users (Right side panel)
6 | Classic | Enable Communities | Goto -> Buid -> Customize -> Communities -> Communities Settings Goto Section "Enable communities" Select check box against "Enable communities" Click Save
7 | Classic | Create Community | Goto -> Buid -> Customize -> Communities -> All Communities Select template "Customer Account Portal" Click Get Started Enter "NCTParentCustomer" in Name field Enter "Customer" in for URL in option field Click Create ( System will redirect Community Workspace ) Click Administration (wrench Icon symbol) Click Settings on the left hand side panel Click Activate Community Button
8 | Classic | Update Contact Record Types | Goto -> Buid -> Customize -> Contacts -> Record Types Click Edit against "Parent" Record Type Uncheck 'Active' Flag Click Save Click Del against "Parent" Record Type Select "Client" for picklist Replace value on records with Click Save Click Edit against "Client" Record Type Change Record Type Label to "Parent" Click Save
9 | Classic | Delete field "Post Code" from Booking Object | Goto -> Setup -> Create -> Objects Click Booking Goto Section "Custom Fields & Relationships" Click Del against field lavel "PostCode" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete
10 | Classic | Delete field "End Date" from Course Object | Goto -> Setup -> Create -> Objects Click Courses Goto Section "Custom Fields & Relationships" Click Del against field lavel "End Date" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete
11 | Classic | Delete field "Start Date" from Course Object | Goto -> Setup -> Create -> Objects Click Courses Goto Section "Custom Fields & Relationships" Click Del against field lavel "Start Date" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete
12 | Classic | Delete field "Venue" from Course Object | Goto -> Setup -> Create -> Objects Click Courses Goto Section "Custom Fields & Relationships" Click Del against field lavel "Venue" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete
13 | Classic | Delete field "Venue" from Sessions Object | Goto -> Setup -> Create -> Objects Click Sessions Goto Section "Custom Fields & Relationships" Click Del against field lavel "Venue" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete
14 | Classic | Publish Sites for Community "NCTParentCustomer" | Goto -> Setup -> Build -> Customize -> Communities -> All Communities Click Builder for Community "NCTParentCustomer" Click Publish which is on top right corner of the page. Click Publish again on the pop up window. Click Got it on the pop up window.

## PostDeploymentSteps
No | Salesforce Mode | Description | Steps | Responsible | User Story | Time | CI | QA | UAT | PROD
1 | Classic | Community license for Profiles | Go to setup-->Quick Find-->Communities -->All Communities -->Go to Workspaces next to community Go to Administration (wrench Icon symbol) Template-->Go to Members list-->Add select Profiles-->Membership co-ordinator--> save
2 | Classic | OWD & Sharing rules creation | Go to setup-->In Administer, click on sharing settings-->click New button of specific object -->Account Sharing Rules-->New--> Label:Read/Write access --> Rule Name : Read_Write_access --> Based on criteria: Owner in Group: Branch co-ordinator group--> owned by members of Group: Branch co-ordinator group--> Share with Group: Branch co-ordinator group--> Default Account, Contract and Asset Access:Read/Write--> Contact Access:Read/Write--> Opportunity Access:Read/Write--> Case Access:Read/Write--> Click Save "Button"
3 | Classic | Sharing Sets | Go to setup -->Quick Find-->Communities Settings-->select Sharing sets-->Click New, Give "Parent Access" as label name -->Sharing set name "Parent_Access"-->Then Select profile "Customer Community Login User" and "Membership coordinator"-->Select objects "Case" Go to Configure Access label- click on setup--> user:account--> select Target :Case-Contact.Account-->Access Level-Read/write--save
4 | Classic | Profile Permissions(FLS, CRUD) | Go to setup -->In Administer, Go to Profiles --> select "Membership coordinator"-->Field-Level Security-->select Custom Field-Level Security Or Standard Field-Level Security --> Provide Basic Access & Data Administration if required--click on "Recurring Donations"[View]-->click on Edit-->select read access Check box-->select Edit Access check box-->save
5 | Classic | Queue | Go to setup-->Quick Find-->Queues-->click on New-->Label: Enquiries Team -->Queue Name : Enquiries Team -->Queue Email:"swathi.kota@csscorp.com" -->Supported Objects:Case -->Queue Members-->" Users"-->click on Save. Remaining Queue Names: Course_Booking_Queue, Branch_Queue,Booking_Enquiry
6 | Classic | Queue | Go to setup-->Quick Find-->Queues-->click on New-->Label: Finance -->Queue Name : Finance -->Queue Email:"Mahanth Garlapati" -->Supported Objects:Payment Schedule -->Queue Members-->" Mahanth Garlapati"-->click on Save.
7 | Classic | Public group | Go to setup-->Quick Find-->Public Groups-->click on New-->Add Label Name:Enquiry Psa Group -->Add Users:Enquires Team-->Click Save Remaining Public Groups:Branch co-ordinator group,Capacity PSA Group,ProjectLego Group,Request to be a volunteer,Volunteer Group,Yoga Co-Ordinator Course drop in Users

## Smoke Test
No | Salesforce Mode | Description | Steps | Responsible | User Story | Time | CI | QA | UAT | PROD
1 | Classic | Creation of record in Account Object | Login sandbox using these credentials: https://test.salesforce.com Go to App in classic : NCT General Click "Account" Tab Create New Button Select any Record type from Branch/Household Account/Organization Continue Fill data for the Mandatory fields inorder to save the record.
2 | Classic | Creation of record in Contact Object | Login sandbox using these credentials: https://test.salesforce.com Go to App in classic : NCT General Click "Contact" Tab Create New Button Select any Record type from Companion/Parent/Practitioner/Volunteer Continue Fill data for the Mandatory fields inorder to save the record.
3 | Classic | Customer Community user creation | Parent Community user creation steps : Go to App in classic : NCT General Click "Contact" Tab Find View(Dropdown) in Contact Object Select "All Parents" from the view, click "Go" . On Detail page of "Contact" record, find "Manage External User" button, click it & select "Enable Customer User" . Check all the Mandatory details filled in User record. Select Profile "Membership Coordinator" Click Save
4 | Classic | Partner Community user creation | Partner Community user creation steps : Go to App in classic : NCT General Click "Account" Tab Find View (Dropdown) in Account Object Select required List View, click "Go" . On Detail page of "Account" record, find "Manage External Account" button, click it & select "Enable As Partner" . Go to Section "Contact". click on "Contact" record. On Detail page of "Contact" record, find "Manage External User" button, click it & select "Enable Partner User" . Select Profile "Practitioner" Click save .
5 | Classic | Manual User creation | Go to Setup Quick find "Users" Click "Users" Click on "New User" Fill the "Mandary data" & enable checkbox "Generate new password and notify user immediately" to save the record.