## PreDeploymentSteps
No | Salesforce Mode | Description | Steps | Responsible | User Story | Time | CI | QA | UAT | PROD | Reference
1 | Classic | Update Sharing Settings | Goto -> Setup -> Administer -> Security Controls - Sharing Settings Click Button "Enable External Sharing Model" Click Edit in "Organization-Wide Defaults" Section as follows Account - Default Internal Access - Public Read / Write Account - Default External Access - Private Contact - Default Internal Access - Private Contact - Default External Access - Private Opportunity - Default Internal Access - Private Opportunity - Default External Access - Private Click Save | Ravi
2 | Classic | Enable Relate Contact to Multiple Accounts | Goto -> Setup -> Build -> Customize -> Accounts -> Account Settings Click Edit Goto Section "Contacts to Multiple Accounts Settings" Select check box against "Allow users to relate a contact to multiple accounts" Click Save | Ravi
3 | Classic | Enable Email Deliverability | This step is required only for sandboxes Goto -> Setup -> Administer -> Email Administration -> Deliverability Goto Section Deliverability Change Access Level to "All Emails" Click Save | Ravi
4 | Classic | Update Case Reason Picklist | Goto -> Setup -> Build -> Customize -> Cases -> Fields Click Field "Case Reason" Goto Section "Case Reason Picklist Values" Click New Enter "Volunteer De-Registration" Click Save | Ravi
5 | Classic | Create my domain | Goto Setup -> Administer -> Domain Management -> My Domain Click Log in (Right side panel) Click Deploy to Users (Right side panel) | Ravi
6 | Classic | Enable Communities | Goto -> Buid -> Customize -> Communities -> Communities Settings Goto Section "Enable communities" Select check box against "Enable communities" Click Save | Ravi
7 | Classic | Create Community | Goto -> Buid -> Customize -> Communities -> All Communities Select template "Customer Account Portal" Click Get Started Enter "NCTParentCustomer" in Name field Enter "Customer" in for URL in option field Click Create ( System will redirect Community Workspace ) Click Administration (wrench Icon symbol) Click Settings on the left hand side panel Click Activate Community Button | Ravi
8 | Classic | Update Contact Record Types | Goto -> Buid -> Customize -> Contacts -> Record Types Click Edit against "Parent" Record Type Uncheck 'Active' Flag Click Save Click Del against "Parent" Record Type Select "Client" for picklist Replace value on records with Click Save Click Edit against "Client" Record Type Change Record Type Label to "Parent" Click Save | Ravi
9 | Classic | Delete field "End Date" from Course Object | Goto -> Setup -> Create -> Objects Click Courses Goto Section "Custom Fields & Relationships" Click Del against field lavel "End Date" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete | Ravi/Ujwal
10 | Classic | Delete field "Start Date" from Course Object | Goto Setup Create Go to Objects Click Courses Goto Section "Custom Fields & Relationships" Click Del against field lavel "Start Date" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete | Ravi/Ujwal
11 | Classic | Delete field "Venue" from Course Object | Goto Setup Create Objects Click Courses Goto Section "Custom Fields & Relationships" Click Del against field lavel "Venue" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete | Ravi/Ujwal
12 | Classic | Delete field "Venue" from Sessions Object | Goto Setup Create Go to Objects Click Sessions Goto Section "Custom Fields & Relationships" Click Del against field lavel "Venue" Select Checkbox against "Yes, I want to delete the custom formula" Click Delete | Ravi/Ujwal
13 | Classic | Publish Sites for Community "NCTParentCustomer" | Goto Setup Build Customize Communities All Communities Click Builder for Community "NCTParentCustomer" Click Publish which is on top right corner of the page. Click Publish again on the pop up window. Click Got it on the pop up window. | MAHANTH
14 | Lightning | Create Membership Collections Target in PaymentHub | Goto AppLauncher StepOrange CPM Tab Menu Choose Setup Goto Section "Extensions-System" ProcessingHub If Payment Processing Authentication details are provided in the below fields( if not present contact StepOrange) Then you will be able to see "Targets" tab. Click "Targets" Tab Click "Add Target" Button Fill the fileds with below information: 1. Name : NCT Membership Collections - S18 2. Target: PaymentHub BACS 3. Type: Manual Click Save. Now click the down arrow beside the created target click settings. Fill the fields with below information: 1: Bank account addition: 30-00-09 2. Bank account number: 02080596 3. Collection file lead time (days) : 3 4. Company name: NCT 5. Company Service User Number: 770552 6. DDI lead time: 10 7. Number of generated files: 1 Click Save | MAHANTH
15 | Lightning | Create Course Fee Collections Target in PaymentHub | Goto AppLauncher StepOrange CPM Tab Menu choose Setup Goto Section "Extensions-System" ProcessingHub If Payment Processing Authentication details are provided in the below fields( if not present contact StepOrange) Then you will be able to see "Targets" tab. Click "Targets" Tab Click "Add Target" Button Fill the fileds with below information: 1. Name : NCT Course Fee Collections - S18 2. Target: PaymentHub BACS 3. Type: Manual Click Save. Now click the down arrow beside the created target click settings. Fill the fields with below information: 1: Bank account addition: 30-00-09 2. Bank account number: 07809225 3. Collection file lead time (days) : 2 4. Company name: NCT 5. Company Service User Number: 836903 6. DDI lead time: 10 7. Number of generated files: 1 Click Save | MAHANTH
16 | Lightning | Create Training Fee Collections Target in PaymentHub | Goto AppLauncher StepOrange CPM Tab Menu choose Setup Goto Section "Extensions-System" ProcessingHub If Payment Processing Authentication details are provided in the below fields( if not present contact StepOrange) Then you will be able to see "Targets" tab. Click "Targets" Tab Click "Add Target" Button Fill the fileds with below information: 1. Name : NCT Training Fee Collections - S18 2. Target: PaymentHub BACS 3. Type: Manual Click Save. Now click the down arrow beside the created target click settings. Fill the fields with below information: 1: Bank account addition: 30-00-09 2. Bank account number: 02080596 3. Collection file lead time (days) : 3 4. Company name: NCT 5. Company Service User Number: 836903 6. DDI lead time: 10 7. Number of generated files: 1 Click Save | MAHANTH
17 | Lightning | Create Course Fee Collections Target in PaymentHub | Goto AppLauncher StepOrange CPM Tab Menu choose Setup Goto Section "Extensions-System" ProcessingHub If Payment Processing Authentication details are provided in the below fields( if not present contact StepOrange) Then you will be able to see "Targets" tab. Click "Targets" Tab Click "Add Target" Button Fill the fileds with below information: 1. Name : NCT Training Fee Collections - S18 2. Target: PaymentHub BACS 3. Type: Manual Click Save. Now click the down arrow beside the created target click settings. Fill the fields with below information: 1: Bank account addition: 30-00-09 2. Bank account number: 02080596 3. Collection file lead time (days) : 3 4. Company name: NCT 5. Company Service User Number: 836903 6. DDI lead time: 10 7. Number of generated files: 1 Click Save | MAHANTH
18 | Classic | Enable Communities | Goto Setup QuickFind Communities Community Settings Select the Checkbox filed Enable Communities In the Domain Name field add value "ournct". Click Save. | MAHANTH
19 | Classic | Creating a Connected App "PaymentConnectedApp" | Goto -> Setup -> Build -> Create -> Click Apps Goto Section Connected Apps Click New Fill the fields with the below information: In Section: Basic Information 1. Connected App Name: PaymentConnectedApp 2. API Name: PaymentConnectedApp 3. Contact Email: users email address who is creating this connected app. In Section: Api (Enable OAuth Settings) 1. Enable OAuth Settings: Select the checkbox 2. Callback URL: https://localhost.com 3. Selected OAuth Scopes: Full Access (full) 4. Require Secret for Web Server Flow: Select the Checkbox Click Save | MAHANTH
20 | Classic | Creating a Connected App "PaymentConnectedApp" | Goto -> Setup -> Build -> Create -> Click Apps Goto Section Connected Apps Click New Fill the fields with the below information: In Section: Basic Information 1. Connected App Name: PaymentConnectedApp 2. API Name: PaymentConnectedApp 3. Contact Email: users email address who is creating this connected app. In Section: Api (Enable OAuth Settings) 1. Enable OAuth Settings: Select the checkbox 2. Callback URL: https://localhost.com 3. Selected OAuth Scopes: Full Access (full) 4. Require Secret for Web Server Flow: Select the Checkbox Click Save | MAHANTH
21 | Classic | Publish Sites for Paymenthub | Goto -> Setup -> User Interface -> Sites and Domains -> Sites Click on "New" button Enter "Payment" value in 'Site Label' Enter "Payment" value in 'Site Name' Select "Active Site Home Page" with "nctMembershipPaymentPage" Click on 'Save' button. | Ujwal
22 | Classic | Add "Visualforce" page in "Payment" Site which created in 15th Step. | Goto -> Setup -> User Interface -> Sites and Domains -> Sites Click on "Edit" button under "Site Visualforce Page" Add "Visualforce Page" -> nctETMembershipPaymentPage, nctMembershipPayementPage, nctPaymentHubErrorMsgPage, nctPaymentHubPage, nctPaymentHubSuccessMsgPage. Click on "Save" button. | Ujwal
23 | Classic | Add "Cutom Label" for the Payment Success and Failure Pages | Goto -> Setup -> User Interface -> Custom Labels Click on "New" button. Enter "PAYMENTSTATUSURL" value under "Short Description" field Enter "PAYMENTSTATUSURL" value under "Name" field Enter "Payment link Site which we did in Step-21" value under "value" field. Click on "Save" button. | Ujwal

## PostDeploymentSteps
No | Salesforce Mode | Description | Steps | Responsible | User Story | Time | CI | QA | UAT | PROD
1 | Classic | Community license for Profiles | Go to setup Quick Find SelectCommunities Selectelect All Communities Go to Workspaces next to community Go to Administration (wrench Icon symbol) Template Go to Members listAdd select Profiles Membership co-ordinator Click on save | Swathi
2 | Classic | OWD & Sharing rules creation | Go to setup Click on sharing settings Click New button of specific object Go to Account Sharing Rules Select New Button Label:Read/Write access Rule Name : Read_Write_access Based on criteria: Owner in Group: Branch co-ordinator group owned by members of Group: Branch co-ordinator group Share with Group: Branch co-ordinator group Default Account, Contract and Asset Access:Read/Write Contact Access:Read/Write Opportunity Access:Read/Write Case Access:Read/Write Click Save "Button" | Swathi
3 | Classic | Sharing Sets | Go to setup Quick Find Communities Settings select Sharing sets Click New, Give "Parent Access" as label name Sharing set name "Parent_Access" Then Select profile "Customer Community Login User" and "Membership coordinator" Select objects "Case" Go to Configure Access label- click on setup User:account Select Target :Case Contact.Account Access Level-Read/write Click on save Button | Swathi
4 | Classic | Profile Permissions(FLS, CRUD) | Go to setup Quick Find In Administer, Go to Profiles Select "Membership coordinator" Select Field-Level Security Select Custom Field-Level Security Or Standard Field-Level Security Provide Basic Access & Data Administration if required Click on "Recurring Donations"[View] Click on Edit Select read access Check box Select Edit Access check box Click save Button. | Nitaj,Tarun,Veerana
5 | Classic | Queue | Go to setup Quick Find Queues click on New Button Label: Enquiries Team Queue Name : Enquiries Team Queue Email:"swathi.kota@csscorp.com" Supported Objects:Case Queue Members: " Users" Click on Save. Remaining Queue Names: Course_Booking_Queue, Branch_Queue,Booking_Enquiry | Swathi
6 | Classic | Queue | Go to setup Quick Find Queues Click on New Button Label: Finance Queue Name : Finance Queue Email:"Mahanth Garlapati" Supported Objects:Payment Schedule Queue Members: " Mahanth Garlapati" Click on Save. | Swathi
7 | Classic | Public group | Go to setup Quick Find Public Groups click on New Add Label Name:Enquiry Psa Group Add Users:Enquires Team Click Save button Remaining Public Groups:Branch co-ordinator group,Capacity PSA Group,ProjectLego Group,Request to be a volunteer,Volunteer Group,Yoga Co-Ordinator Course drop in Users | Veera
8 | Classic | Create Site "PaymentLink" | Create Site "PaymentLink" Goto -> Setup -> Develop -> Lightning Components -> Sites Click New Fill the following fields with below values. 1. Site Label : PaymentLink 2. Site Name: PaymentLink 3. Site Contact: Current_User (This needs to be updated in future) 4. Default Web Address: "PaymentLinkProcessor" 5. Active: Select the checkbox 6. Active Site Home Page: PaymentLinkProcessor and leave rest of the fields to the default. Click Save. | MAHANTH
9 | Lightning | Update Site URL values for Stripe Payment in Payment Hub. | Goto Select App Launcher Click on "StepOrange CPM" From TabMenu Click on Setup Goto Section "Extensions PSP" Click "PaymentHub-Stripe" Remove the production url value from "Push URL" field. Goto Setup Quick Find Select Sites Copy the "Site URL" value for Site "CreditCardPayment". Now paste that value in the "Push URL" field on "PaymentHub-Stripe". Once done the "Webhook URL" field also automatically gets updated with the latest url pasted just now. Remove the value for field "Publishable Key(Production)". Update the value for filed "Publishable Key(Test)" with the value that is in PreUAT. Also Enable the slidebar for field "IsTest". | MAHANTH
10 | Lightning | Login page enable | Go to setup Quick Find Click on All Communities Click on Workspaces Select Administration Go to Login&Registration go to Registration Page Configuration Enable the check box Allow external users to self-register Registration Page Type: Visualforce Page : ParentCommunitySelfReg Profile: Membership coordinator select Account Click on save | Swathi
11 | Lightning | Signup Page added | Go to setup Quick Find Click on All Communities Click on Workspaces Select Administration Go to Pages Go to Force.Com Click on Edit Click on Self Registration Page and add ParentCommunitySelfReg Click on Save | Swathi
12 | Lightning | Added Data source field for Transaction object | Go to setup Object Manager Enter in Quick Find "Transaction" go to Fields & Relationships click on New Button Check button Picklist Button Field Label:Data Source Field Name: Data_Source select Radio button:Enter values, with each value separated by a new line Add these values: Salesforce,CARE,Intrabiz Click on checkbox :Use first value as default value click next select Visible check box and select next button Click checkbox : Transaction Layout Click Save button | Swathi
13 | Lightning | Added Data source field for cpm__Transaction__c object | Go to setup Object Manager Enter in Quick Find "Transaction" API Name " cpm__Transaction__c" go to Fields & Relationships click on New Button Check button Picklist Button Field Label:Data Source Field Name: Data_Source select Radio button:Enter values, with each value separated by a new line Add these values: Salesforce,CARE,Intrabiz Click on checkbox :Use first value as default value click next select Visible check box and select next button Click checkbox : Transaction Layout Click Save button | Swathi
14 | Lightning | Add visualforce Home page into builder | Go to setup Quick find go to All Communities click on Builder option select Component option go to Visualforce option Drag in to Content section Give the ParentCommunityHome Page in Visualforce Page Name Then click on Publish option | Swathi
15 | Lightning | Add Logo for signup Page | Go to setup Quick Find Click on All Communities Click on Workspaces Select Administration Go to Login&Registration go to Branding Options Logo file : Choose file from local system Click on Save button | Swathi
16 | Lightning | Add visualforce page into HELP tab | Go to setup Quick find go to All Communities click on Builder option select Navigation Menu Click on Edit Default Navigation Click on Add Menu Item give Name: Help Type:CommunityPage Page:NCTHelpTicket click on check box Publicly available Click on save button Then click on Publish button | Swathi
17 | Lightning | Add Branding for signup Page | Go to setup Quick Find Click on All Communities Click on Workspaces Select Administration Go to Login&Registration go to Branding Options select Branding options Give Background #FFFFFF Login Button: #1797C0 Click save button. | Swathi
18 | Lightning | Add Branding into Builder page | Go to setup Quick Find Click on All Communities Click on Workspaces Select Administration Go to Builder Click on Theme option Go to Images Select General Company logo Add NCT 1st 1000 Days logo from our local system Click on Publish | Swathi
19 | Lightning | Add Contact Preferences values for contact object | Go to setup Click on object Manager Go to Quick Find Enter contact Click on Fields & Relationships Go to Quick Find and Enter Contact Preferences Go to values Click on NEW button Enter Post,Email,Telephone,SMS Text values select All Record Types Click on save | Ujwal
20 | Classic | Profile Access for "Custom Application" | Go to setup Quickfind “Profiles” click profile name click Edit Button Under "Custom App Settings" section , make sure NCT General Lightening app as "Default" access. | Asha Latha
21 | Classic | Rename Label Name for Tabs : “Account” & Contact” | Go to setup Quick find “Tabs” Under “Build section” Go to “Rename Tabs & Labels” Edit Next to Accounts Tab Name, provide plural as Account. Edit Next to Contacts Tab Name, provide plural as Contact. Click save. | Asha Latha
22 | classic | Membership custom Visualforce Tab | Go to setup Quick find : Tabs Go to section : “Visualforce Tabs” Click New Follow step 1: Enter the Details for “Visualforce Tab” Provide Visualforce page : nctETMembershipPaymentPage Tab Label: Membership Tab Name: Membership Tab style: Form Go to “Next” Provide profile level access : “System Administrator, Enquiry PSA”, Enquiries Team” & App Level permissions : “NCT General” & “NCT General lightening” Click save. | Asha Latha
23 | Classic | Tab for Payment Link | Go to setup Quick find “Tabs” Click New Select Object from drop down “Payment Link” Provide “Tab style” – Globe Click “Next” Button Give profile level permission access to “System Administrator” & App level permission to “NCT General” & “NCT General Lightening”. Click save | Asha Latha
24 | Classic | Account Contact Relationship | Go to Seup Quick find “Account Contact Relationships” Go to Fields Under “Account Contact Relationship Fields” . Go to “Roles” Multipicklist & add these values : “Branch Coordinator”, “Branch Treasurer”, “Branch Sub-Coordinator”, “Regional Coordinator”, “Volunteer” . Click Save. | Asha Latha
25 | Lightning | Update Stripe for PaymentHub | Goto -> AppLauncher Choose SetpOrange CPM Choose Setup from TabMenu Goto Section Extesnions PSP Click on PaymentHub-Stripe Remove the Push URL field Value Update the Push URL value by following below steps: 1. Go -> Sites from Salesforce SetupMenu 2. Copy the site url of the CreditCardPayment site. Now coming back to the PaymentHub-Stripe. Paste the copied site url of the CreditCardPayment site in the Push URL filed . Now the webhook URL field will automatically gets updated. Remove the value from field Publishable Key (Production), this should be blank in test environments. Also make sure that Secret Key(Production) field should be blank in test environments. Update the field Publishable Key (Test) with the value that is in PreUAT Is Test field should be enabled Log Requests fields should be enabled. Click Save. | MAHANTH
26 | Lightning | Create Target NCT Giftaid in PaymentHub | Goto AppLauncher StepOrange CPM Tab Menu choose Setup Goto Section "Extensions-System" Click ProcessingHub If Payment Processing Authentication details are provided in the below fields( if not present contact StepOrange) Then you will be able to see "Targets" tab. Click "Targets" Tab Click "Add Target" Button Fill the fileds with below information: 1. Name : NCT Giftaid 2. Target: PaymentHub GiftAid Click Save. Now click the down arrow beside the created target click settings. Fill the fields with below information: 1: Authorised Official First Name: Hannah 2. Authorised Official Phone Number: 02087522336 3. Authorised Official Postal Code : BS8 3NG 4. Authorised Official Surname: Cook 5. Charity Registration Number: 801395 6. Charity Regulator: CCEW 7. HMRC Charities Reference: X98821 8. Charity Name: The National Childbirth Trust 9. Records per file: 500000 10. Test Mode: Should be Enabled 11. Upload Copy To Chatter: Should be Enabled 12. XML API Username: 8ag4j9cbvvc7 Click Save | MAHANTH

## Smoke Test
No | Salesforce Mode | Description | Steps | Responsible | User Story | Time | CI | QA | UAT | PROD
1 | Classic | Creation of record in Account Object | Login sandbox using these credentials: https://test.salesforce.com Go to App in classic : NCT General Click "Account" Tab Create New Button Select any Record type from Branch/Household Account/Organization Continue Fill data for the Mandatory fields inorder to save the record.
2 | Classic | Creation of record in Contact Object | Login sandbox using these credentials: https://test.salesforce.com Go to App in classic : NCT General Click "Contact" Tab Create New Button Select any Record type from Companion/Parent/Practitioner/Volunteer Continue Fill data for the Mandatory fields inorder to save the record.
3 | Classic | Customer Community user creation | Parent Community user creation steps : Go to App in classic : NCT General Click "Contact" Tab Find View(Dropdown) in Contact Object Select "All Parents" from the view, click "Go" . On Detail page of "Contact" record, find "Manage External User" button, click it & select "Enable Customer User" . Check all the Mandatory details filled in User record. Select Profile "Membership Coordinator" Click Save
4 | Classic | Partner Community user creation | Partner Community user creation steps : Go to App in classic : NCT General Click "Account" Tab Find View (Dropdown) in Account Object Select required List View, click "Go" . On Detail page of "Account" record, find "Manage External Account" button, click it & select "Enable As Partner" . Go to Section "Contact". click on "Contact" record. On Detail page of "Contact" record, find "Manage External User" button, click it & select "Enable Partner User" . Select Profile "Practitioner" Click save .
5 | Classic | Manual User creation | Go to Setup Quick find "Users" Click "Users" Click on "New User" Fill the "Mandary data" & enable checkbox "Generate new password and notify user immediately" to save the record.